# Project Plan — Publishing Power, Pressure & Choice (for Microsoft Planner)

Internal project to build the interactive and publish it on the AMES Australia website. Built for Microsoft Planner (Premium). No budget/procurement tasks.

Schedule: the approved content was received on Wed 1 July 2026, and the project is to be finished by Fri 31 July 2026 — including QA, the Education + PVAW review, and fixes. Google Analytics is the final stage, added after launch. It is an aggressive one‑month schedule, so several tracks run in parallel (see §2).

Kept deliberately lean — 21 tasks so the board stays easy to scan. The development build is a few generic tasks; the detail lives inside each task’s checklist.

How this document is laid out: 1. Overview — who’s involved and the shape of the project. 2. Timeline (July 2026) — dated, with the parallel tracks. 3. Master task list — every task, numbered, with owner, duration and dependencies. 4. Set it up in Planner — buckets, labels, goals, dates, and how to add dependencies. 5. Task checklists — the detail for each task.

## 1. Overview

| Role | Who | Does |
| --- | --- | --- |
| Me (PM/Dev) | You | Project management and development — build the game, accessibility, analytics code, fixes, go‑live coordination |
| Edu team | Stakeholder | Delivered the finalised content (1 Jul); joins the single review |
| PVAW team | Stakeholder | Violence‑prevention / pedagogy oversight; joins the single review |
| Digital team | Internal | QA and the website side — hosting, Drupal embed, security headers, scans, GA setup, deploy |
| IT / Security | Internal | Reviews and signs off the security assessment |

What shapes the plan: - Content received 1 Jul → finish 31 Jul. The build starts on the content (task 4) and everything must land inside July, including QA, the Edu + PVAW review and fixes. - One stakeholder review (Edu + PVAW together, task 15). QA and the IT security sign‑off are separate technical gates, not extra content reviews. - Google Analytics is the final stage (tasks 20–21). The site launches without analytics to hit the date, then GA4 is added straight after — so analytics is not part of QA or the launch smoke‑test.

## 2. Timeline — July 2026

Content received Wed 1 Jul, target finish Fri 31 Jul. To fit the month, the Digital‑team integration track overlaps the build tail, and QA / the stakeholder review run on the near‑final build.

| Phase (bucket) | Dates (2026) | Notes |
| --- | --- | --- |
| 1 · Initiation & Sign‑off | Wed 1 Jul | Quick kickoff the day content arrives |
| 2 · Content Intake & Build | Wed 1 Jul – Thu 16 Jul | The long pole (~2.5 weeks) |
| 3 · Security & Integration | Wed 16 Jul – Fri 24 Jul | Digital team; starts alongside the build tail |
| 4 · QA | Wed 22 Jul – Fri 24 Jul | Functional, cross‑browser, accessibility |
| 5 · Stakeholder Review & Sign‑off (Edu + PVAW) | Mon 27 Jul – Tue 28 Jul | One consolidated review + fixes |
| 6 · Launch & Handover | Wed 29 Jul | Go‑live readiness + publish + smoke test |
| 7 · Analytics & Privacy (final stage) | Thu 30 – Fri 31 Jul | GA4 added last, after launch |

Key dates - Wed 1 Jul — approved content received (build trigger). - Thu 16 Jul — build complete (incl. accessibility + internal QA). - ~Fri 24 Jul — security sign‑off + QA done. - Tue 28 Jul — Edu + PVAW review complete and fixes done. - Wed 29 Jul — go live. - Fri 31 Jul — Google Analytics live (final stage); project complete. (Monitoring & support then continues into early August.)

## 3. Master task list (with dependencies)

How to read it: # is the task number. Depends on lists the number(s) that must finish first (a dash = no predecessor). Days = working‑day estimate — note phases overlap (see §2), so the calendar is shorter than the durations added up. Tasks are in build order.

| # | Task | Phase | Owner | Pri | Days | Depends on |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Confirm scope, roles & the single review | Initiation & Sign‑off | Me (PM/Dev) | High | 1 | — |
| 2 | Confirm AMES technical prerequisites | Initiation & Sign‑off | Digital team | High | 1 | — |
| 3 | Set up the Planner plan & link docs | Initiation & Sign‑off | Me (PM/Dev) | Medium | 1 | — |
| 4 | Receive finalised game content (Edu team) — 1 Jul | Content Intake & Build | Edu team | High | 1 | — |
| 5 | Build the game visuals & world | Content Intake & Build | Me (PM/Dev) | High | 4 | 4 |
| 6 | Build the game flow & interface | Content Intake & Build | Me (PM/Dev) | High | 3 | 5 |
| 7 | Wire in the finalised content & the three outcomes | Content Intake & Build | Me (PM/Dev) | High | 2 | 6 |
| 8 | Pedagogy guardrail check (with PVAW) | Content Intake & Build | Me (PM/Dev) + PVAW | High | 1 | 7 |
| 9 | Accessibility (WCAG 2.1 AA) & internal build QA | Content Intake & Build | Me (PM/Dev) | High | 2 | 7 |
| 10 | Provision hosting & apply security headers/CSP | Security & Integration | Digital team | High | 2 | 9 |
| 11 | Embed in the Drupal page & run security scans | Security & Integration | Digital team | High | 2 | 10 |
| 12 | IT/Security review & sign‑off | Security & Integration | IT/Security | High | 1 | 10, 11 |
| 13 | QA — functional, cross‑browser/device & accessibility | QA | Digital team | High | 2 | 11 |
| 14 | Fix issues found in QA | QA | Me (PM/Dev) | High | 2 | 13 |
| 15 | Stakeholder review & sign‑off (Edu + PVAW) | Stakeholder Review & Sign‑off | Edu + PVAW | High | 2 | 14 |
| 16 | Address review feedback | Stakeholder Review & Sign‑off | Me (PM/Dev) | High | 2 | 15 |
| 17 | Go‑live readiness review | Launch & Handover | Me (PM/Dev) | High | 1 | 12, 16 |
| 18 | Publish, announce & smoke test | Launch & Handover | Digital + Me | High | 1 | 17 |
| 19 | Monitor, support & documentation handover | Launch & Handover | Me (PM/Dev) | Medium | 3 | 18 |
| 20 | Set up analytics & events (GA4) + data‑minimisation | Analytics & Privacy | Me (PM/Dev) | Medium | 2 | 18 |
| 21 | GA4 property, consent, privacy notice & verify | Analytics & Privacy | Digital + Me | High | 1 | 20 |

The critical path (the chain that sets the end date): 4 → 5 → 6 → 7 → 9 → 10 → 11 → 13 → 14 → 15 → 16 → 17 → 18 → 20 → 21. Google Analytics (20–21) is the tail, added after launch (18).

## 4. Set it up in Planner

### 4.1 Buckets and labels

- Buckets (columns) = the 7 phases: Initiation & Sign‑off · Content Intake & Build · Security & Integration · QA · Stakeholder Review & Sign‑off · Launch & Handover · Analytics & Privacy (final).

- Labels (colour tags), one per task by owner: Me (PM/Dev) · Edu team · PVAW team · Digital team · IT/Security.

- Goals (Premium → Goals): G1 Live on ames.net.au by 31 Jul · G2 WCAG 2.1 AA · G3 IT security sign‑off · G4 Analytics live & privacy‑compliant (final stage).

### 4.2 Adding the tasks

Fastest: in each bucket, + Add task → paste that bucket’s task names from planner-tasks-by-bucket.txt (Planner creates them all at once). Full steps and the automated option are in PLANNER_IMPORT_GUIDE.md. Then add each task’s checklist (§5), owner, priority, duration and dates.

### 4.3 Dates and dependencies (Planner Premium)

Set the dates from §2. Give task 4 a start date of 1 Jul 2026, then set each bucket’s start from the §2 calendar. Because the month is tight, set the phase start dates directly (parallel tracks) rather than relying purely on finish‑to‑start chaining — the dependencies below capture the must‑finish‑before order within each track.

Add the dependencies (Grid view): 1. Switch to Grid view; add tasks in the table order so row numbers match the # column. 2. Add the “Depends on” column (+ Add column → Depends on). 3. In each task’s Depends on cell, type the predecessor number(s) — comma‑separated, e.g. enter 10, 11 on task 12 (IT/Security review & sign‑off).

Or draw the links in Timeline (Schedule) view: grab the round link handle on a bar’s right edge and drag to the successor. Work down the critical path (4 → 5 → 6 → 7 → 9 → 10 → 11 → 13 → 14 → 15 → 16 → 17 → 18 → 20 → 21).

Planner uses finish‑to‑start links. Because the calendar overlaps phases to fit July, the durations added up are longer than the calendar — trust the §2 dates for scheduling.

## 5. Task checklists (the detail for each task)

Owner, duration and dependencies are in the master table (§3). Paste these into each task’s Checklist in Planner.

### Phase 1 — Initiation & Sign‑off (Wed 1 Jul)

- 1. Confirm scope, roles & the single review — in/out of scope and success measures (launch by 31 Jul, WCAG AA, IT sign‑off); roles (Me = PM + developer; Edu = finalised content; PVAW = oversight; Digital = QA + integration; IT = security sign‑off); agree the one review.

- 2. Confirm AMES technical prerequisites — Drupal CSP?; cookie‑consent tool; hosting choice & target URL.

- 3. Set up the Planner plan & link docs — buckets, labels, goals; attach the docs.

### Phase 2 — Content Intake & Build (Wed 1 Jul – Thu 16 Jul)

- 4. Receive finalised game content (Edu team) — final copy, choices and structure delivered 1 Jul; confirm completeness before build. (Build trigger.)

- 5. Build the game visuals & world — set up the app; procedural tree (trunk, branches, roots) with stage‑based growth; living landscape (sky, hills, meadow, sun, clouds, ambient motion); health‑driven states — decline (leaf fall, thinning, bark, snag) and watering / heal feedback.

- 6. Build the game flow & interface — branching logic & game state (choices, forward/back navigation, outcome resolution); UI panel & responsive layout (question, choices, insight, progress, support line; desktop panel vs mobile bottom‑sheet); synthesised audio (mute toggle) and save/resume progress.

- 7. Wire in the finalised content & the three outcomes — load the Edu copy and branches end‑to‑end; the three outcomes (Healthy / Healing / Under strain) plus the path recap.

- 8. Pedagogy guardrail check (with PVAW) — support line on every screen; no “wrong answer” on pressures/impacts; harm never heals; no shame language; the damaged outcome is reversible.

- 9. Accessibility (WCAG 2.1 AA) & internal build QA — keyboard nav & focus, labels/text alternatives, contrast, reduced‑motion, screen‑reader run‑through; cross‑device polish and fixes; static export (output:'export'; npm run build → out/) tested locally.

### Phase 3 — Security & Integration (Wed 16 Jul – Fri 24 Jul; Digital team, overlaps the build tail)

- 10. Provision hosting & apply security headers/CSP — subdomain (recommended) or subfolder; DNS, HTTPS, MIME/cache; deploy out/; CSP, HSTS, X‑Content‑Type‑Options, frame‑ancestors, Referrer‑Policy, Permissions‑Policy, tuned to the build.

- 11. Embed in the Drupal page & run security scans — page/block, responsive iframe, allow <iframe> in the text format, title/allow attributes; npm audit / SCA; OWASP ZAP; manual XSS test on the commitment field.

- 12. IT/Security review & sign‑off — walk the risk register; complete the go‑live checklist; record approval.

### Phase 4 — QA (Wed 22 Jul – Fri 24 Jul) · no analytics here — GA is the final stage

- 13. QA — functional, cross‑browser/device & accessibility — all branches & three outcomes, back/restart, persistence, audio, edge cases; Chrome/Edge/Safari/Firefox, iOS & Android, iframe scaling, keyboard focus; screen reader / keyboard‑only / contrast / reduced‑motion.

- 14. Fix issues found in QA — triage and fix; redeploy; retest with the Digital team.

### Phase 5 — Stakeholder Review & Sign‑off (Mon 27 Jul – Tue 28 Jul; the single review)

- 15. Stakeholder review & sign‑off (Edu + PVAW) — one consolidated review of the QA’d game; confirm it matches the finalised content; pedagogy, guardrails, support line; capture one set of feedback; record sign‑off.

- 16. Address review feedback — implement agreed changes; re‑confirm if needed.

### Phase 6 — Launch & Handover (Wed 29 Jul)

- 17. Go‑live readiness review — tick the security go‑live checklist; QA + accessibility done; IT sign‑off and stakeholder sign‑off both in.

- 18. Publish, announce & smoke test — publish the page, add to menu/nav, internal comms, optional soft launch; then verify the live page, headers live, support line visible. (Analytics is added next, in the final stage.)

- 19. Monitor, support & documentation handover — watch feedback/error reports and triage with the Digital team (first weeks), patch cadence; store all docs in the AMES repo / SharePoint; lessons learned; future ideas with Edu/PVAW. (Continues into early August.)

### Phase 7 — Analytics & Privacy (Thu 30 – Fri 31 Jul — the final stage)

- 20. Set up analytics & events (GA4) + data‑minimisation — add gtag + lib/analytics to the live site; fire game_start, choice_made, outcome_reached, commitment_written, restart; data‑minimisation: no free‑text/commitment sent, only fixed labels, kind and hidden health.

- 21. GA4 property, consent, privacy notice & verify — GA4 data stream / Measurement ID; consent (Consent Mode v2 / banner); IP anonymisation; update the privacy policy; verify events in DebugView/Realtime (no free‑text captured); mark key events; basic reports.

## Assumptions

- Content received 1 Jul 2026; target finish 31 Jul 2026. Working‑day estimates for one developer; phases overlap (parallel tracks) so the calendar (§2) fits the month even though the durations added up are longer.

- You are PM + Developer; the Digital team and stakeholders own the rest.

- One stakeholder review (task 15, Edu + PVAW together) on the QA’d build.

- Google Analytics is deliberately the final stage (tasks 20–21): the site launches without analytics on ~29 Jul, then GA4 + consent are added ~30–31 Jul. The launch page has no cookies until then, so no consent is needed at launch. Analytics is therefore not part of QA or the launch smoke‑test.

- “Digital team” covers QA and the website side (hosting, Drupal embed, headers, scans, GA setup, deploy). If they only do QA, reassign the web tasks to yourself.

- No budget/procurement tasks (internal project).